## Sheet1
ACTIVITY CHART / WORK PLAN
NAME OF THE PROJECT
ACTIVITY | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
| JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE
Land Acquisition
Selection of land
Request for land acquisition
Preparation of details of land & owners
Payment to Revenue Department
Notification under section 4
Notification under section 17
Award
Notification by Revenue department
Payment to land owners
Transfer of land
Possession of land
Any other activity
Recruitment
Advertisement in the press
Receipt of applications
Scrutiny of applications
Constitution of recruitment committee
Issuance of call letters
Test/interviews
Selection
Approval of competent authority
Issuance of appointment letters
Joining
Any other activity
Appointment of Consultants
Preparation of TOR of consultants
Approval of TOR
Advertisement in the Press
Approval by competent authority
Issuance of offer letter
Agreement with consultant
Joining of consultant
Any other activity
CONSTRUCTION BY P.W.D / C&W
Letter to PWD/C&W
Appointment of an Engineer
Preparation of Line Plan
Approval of Line plan
Sub-soil investigations
Preparation of Detailed Architectural Drawings
Structural Design
Technical Approval
Preparation of tenders
Floating of tenders
Opening of tenders
Scrutiny of tenders
Approval of tenders
Award of work
Mobilization of contractor
Layout of construction design
Structural works
Plaster works
Wood/Electric works
Utility connections
Finishing works
Any other activity
Construction other than PWD
Advertisement for pre-qualification of contractors
Receipt of applications
Scrutiny of applications
Pre-qualificaton of contractors
Issuance of tenders
Recepit of Tenders
Opening of Tenders
Scrutiny of Tender
Approval by competent authority
Award of works
Submission of Bid Bond, Perfomance Bond etc.
Contractor mobilized
Layout of construction design
Structural works
Plaster works
Wood/Electric works
Utility connections
Finishing works
Any other activity
ROAD Construction
Advertisement for pre-qualification of contractors
Receipt of applications
Scrutiny of applications
Pre-qualificaton of contractors
Issuance of tenders
Receipt of tenders
Opening of tenders
Scrutiny of tenders
Approval by competent authority
Award of work
Submission of Bid Bond, Performance Bond etc.
Contractor mobilized
Site clearence
Sub grade preparation
Laying of sub Base
Laying of Base
Carpetting/TST
Darins
Culverts
Bridges
Any other activity
Procurement of Equipment/Goods
Constitution of Procurement Committee
Preparation of list of goods
Detail specification of goods
Approval of competent authority
Preparation of Tenders
Advertisement in the Press
Receipt of Bids
Opening of Bids
Scrutiny of Bids
Approval of competent authority
Placement of orders
Pre-delivery inspection
Delivery of equipment/goods
Installation
Operation
Any other activity
Human Resource Development
Advertisement
Receipt of applications
Scrutiny of applications
Test of Candidates
Selection/Placement of Candidates
Admission in Institutes
Completion of formalities (Visa etc)
Departure of Candidates

## Sheet2
ROAD Construction
Advertisement for pre-qualification of contractors
Receipt of applications
Scrutiny of applications
Pre-qualificaton of contractors
Issuance of tenders
Receipt of tenders
Opening of tenders
Scrutiny of tenders
Approval by competent authority
Award of work
Submission of Bid Bond, Performance Bond etc.
Contractor mobilized
Site clearence
Sub grade preparation
Laying of sub Base
Laying of Base
Carpetting/TST
Darins
Culverts
Bridges
Any other activity