## Slide 1
Implementation of Programmes
Session 6

## Slide 2: Session Objectives
Identify key considerations when work planning
Understand key aspects related to the management of programmes
Understand how to select the appropriate implementation modalities to carry out activities
Identify risks and risk management approaches to programme delivery

## Slide 3: Work planning considerations
Involvement of counterparts and development partners
Review outputs and strategies as outlined in strategic plans (Strategy Notes, CPD)
Determine activities for corresponding strategies identified
Input requirements to carry out activities
Time required to carry out activities
Implementation modalities
Partners and responsible persons
Funding sources and gaps
Presentation in VISION
Quality assurance
Notes: This outlines some of the considerations that staff should think about when developing workplans
Workplans on activities to be developed with government counterparts, CSOs, UN agencies and other partners cannot be undertaken by UNICEF alone – they should be developed with key stakeholders
The reference for the development of annual, rolling or multi-year workplans should be strategic planning documents, such as the CPD, CPAP, One Programme, Joint UN Work plan. Work plans draw from the results and strategies outlined in these strategic multi-year planning documents.
Consider all input requirements to undertake activities (cash, supplies, technical assistance). Are all available in sufficient quantities?
What will be the most important implementation modalities
Will activities be financed from regular resources, other resources? Do we have any funding gaps?
Once plans have been done outside the management system, they have to be correctly inputted into VISION – how is this assured?
What quality assurance processes exist to ensure the quality, coherence of workplans

## Slide 4: Input planning
Cash
Supplies
Technical Assistance
Determining what resources (people, cash, and supplies) are needed
When they will be needed to implement activities as outlined in workplans
In UNICEF, there are three primary types of inputs:
Notes: Technical assistance
  Provided directly by UNICEF staff to partners to support the development of activities, including policy advice
  Provided by consultants working with UNICEF or with government that UNICEF assists to recruit and fund
2. Cash
  Transferred to implementing partners to carry out activities
  Utilized by UNICEF offices to directly carry out activities
3. Supplies
  Transferred to implementing partners to carry out activities
  Purchased for/on behalf of governments
  Utilized internally by UNICEF offices

## Slide 5: Implementation Modalities
UNICEF generally applies one or more of four implementation modalities to achieve a result:
Working with Government
Working with Civil Society Organizations
Working with Other UN Agencies
UNICEF Directly implementing an activity
Considering the most suitable modality takes into account the specific needs of an intervention and operating environment, and comparative advantage to support achievement of results
Notes: Worth thinking about: The programme strategy directs the formulation of activities and the determination of the most appropriate implementation modality. For instance, moving towards systems development rather than just training health workers or teachers in isolation, and what that entails, with regards to planning additional activities

## Slide 6: Considerations in determining modalities and strategies
Economy – obtaining inputs of appropriate quality at the right price
Efficiency – timely allocation and use of resources to achieve outputs
Effectiveness – the most appropriate strategy and modality for achieving results
Notes: Economy: Is UNICEF or a potential partner best placed to obtain inputs of appropriate quality at the right price?
Efficiency: How well does UNICEF versus a potential partner or vendor undertake activities to convert inputs into quality outputs?
Effectiveness: Is it more likely that desired outcomes, including an equity-based approach to programme delivery, will be achieved if one implementation approach is chosen over another?
Other criteria could be considered, especially for strategies:
Sustainability
Feasibility
Complementarity

## Slide 7: What are we managing when implementing?
Strategies and activities
Relationships with stakeholders
Implementing partners
Media and information
Financial resources
Human resources/staff
Supplies and equipment
Compliance with funding agreements
Internal processes
Risks
Knowledge

## Slide 8: Monitoring is Managing
Tracking progress against planned activities
  utilization of inputs (cash, supplies, technical assistance, time),
  adequacy of processes and activities (scope of work)
  performance of critical personnel and partners
  Identification of outputs
Identifying and addressing bottlenecks / constraints
Using key decision points to facilitate adjustments
Documenting and sharing information
Notes: Time is also a key input that is often neglected.

## Slide 9: Group work on case studies
For one of your identified outputs indicate:
Major activities that have to be implemented to achieve the output
The implementation modality(ies) you will use
How you will select your implementing partner (Be specific: Implementation Partner, CSO, Direct, UN) what criteria will you use?
Which elements will require close management to enable timely achievement of results
Identify 2-3 -- risks in achieving your outputs and how you will mitigate them
  Pay specific attention to comparative advantage, efficiency, effectiveness and sustainability

## Slide 10: Key Messages
Careful management of all aspects of programme delivery is crucial for the efficient and effective achievement of results.
Effective implementation depends on thorough selection of implementation strategies, implementation modalities and partners.
Effective implementation monitoring entails tracking progress against time, budget and scope.
Identifying risk, discussing risk tolerance and designing risk mitigation measures is crucial to effective implementation.