## Slide 1: RBM Cycle
Key Steps

## Slide 2: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning

## Slide 3: Evidence & Analysis
Identifying deprivations:
  Who is being deprived of their rights?
  How many are they?
  What is their profile (male/ female/ ethnicity, economic/ education/ etc)
  Where are they located?
  What other deprivations are they suffering from?
  What are the patterns of deprivations – getting better or worse

## Slide 4: Strategic Planning
This will generally include:
c
Strategic Planning is a disciplined approach to develop a multi-year vision of what results will be achieved and how they will be achieved
  Understanding the Causes of deprivations and Prioritizing issues to be addressed by UNICEF Action
  Establishing a Theory of Change (ToC) for the problem or deprivation
  Developing a Strategic Plan with a Results Framework
  Aligning Results, Strategies and Funding
1
3
2
4
Notes: There are four main stages in the strategic planning process. This session covers the first step, which is Prioritising and developing causalities.
Programme planning is an iterative process, whereby results, strategies and the proposed course of action are adjusted until there is a reasonable expectation that the planned results can be achieved with the selected interventions, strategies and the available resources.
Once programme areas have been identified and prioritized to make a change in the well-being and development status of children, (ex: improving early childhood education), then it is imperative to go through the necessary steps to properly design the programme.
In considering Strategic Planning, we start off by looking at how we prioritise and how a systematic approach should be used when considering the issues and deprivations UNICEF will work to address alongside partners.

## Slide 5: Prioritization
Prioritization
What should we prioritize and why?
When do we prioritize?
How do we prioritize?
Notes: Each questions to be asked one by one and solicit feedback from participants. Animation provided for each of the question to come up after clicking.

## Slide 6: Prioritization
Priority issues to be addressed
UNICEF cannot address all deprivations. It needs to prioritize based on its comparative advantage using 5 key filters:
Criticality of national
challenges and inequities
Mandate: Strategic Plan, alignment with global / sectoral priorities
Position to act better than other partners
Capacities and resources (human, financial, knowledge, technology, partners)
Lessons learned, knowledge of what works and what does not
SHARPENING FOCUS
1
2
3
4
5
Notes: UNICEF cannot address all deprivations. It has to focus its interventions on a few priority areas
Central to prioritization is the notion of UNICEF’s comparative advantage having the mandate, resources and capacity to act effectively
Five key filters can support prioritization and selection of programme areas that UNICEF should address in a CPD
A “prioritization funnel” helps guide consideration of the mutually reinforcing criteria or filters to choose and select projects and programmes, including their strategies.

## Slide 7
Causality

## Slide 8: Why pay attention to causality?
Causality Analysis supports the identification of the immediate, underlying and structural causes of the deprivations which UNICEF has chosen to address
Causality requires systematically asking “why?” through a hierarchy of issues and identifying the causes for deprivation at each level in the hierarchy
A well-developed causal analysis will affect and help to tailor strategic responses
Notes: In building a situation analysis to understand contexts, deprivations, inequities and the realisation of child rights, the determinant framework can be used to strengthen causality by highlighting the causes and consequences of barriers to critical conditions necessary to address inequities and narrow gaps between groups.
Systematically asking the question “who” and “why?”, based on the available data/information will help to move from immediate causes of a situation, to considering the underlying and structural causes of these manifestations as they affect different groups in society.
The determinant framework (make reference to the MoRES ten determinant framework to be distributed as handout) can be used in developing causality, particularly in analyzing the range of issues likely to have a bearing on deprivations and the causes of inequities.
Causality enables understanding of the immediate causes of a situation to considering its underlying and structural causes as it affects different groups in society.
Evidence from the analysis of bottlenecks and barriers in achieving desired results should inform the causal analysis

## Slide 9: Prioritization
Prioritization
How do we develop causality around an issue?
Where do we get the information from?
Who is involved?
How can we be sure of the quality of the analysis?
Notes: Questions to be posed in plenary and solicit feedback from participants.

## Slide 10: Template for Developing Causality
why? because
why? because
why? because
Social organization, policies, inequitable distribution of resources, governance, political issues, culture
Shortfalls in social services,
lack of access, harmful beliefs, practices
Near and direct cause,
most obvious link
Negative outcome, a right not respected, protected or fulfilled
Underlying causes
Key Deprivation
Immediate causes
Structural causes
Notes: A causal analysis allows for different streams of a problem to be examined in-depth. Causes are not linear, but are often a complex interaction of multiple streams that reinforce each other. More immediate causes are often easier to address, while more structural causes are more difficult and often longer-term, but tend to provide more sustainable solutions and results.

## Slide 11: Lenses to develop causality
Human rights
Gender
Equity
Ten determinants of the coverage of services
Risks
10
LENSES
Notes: Make reference to the hand-out notes on each of these lenses.

## Slide 12: Sample
Under-lying causes
Lack of legal
structure/
framework for
birth registration
Lack of motivation
by parents to register
their children
Low rate of birth registration
More than 90% of children remain unregistered
Deprivation
Immediate causes
Structural causes
Inadequate
“reinforcement”
to register births
Costly birth
registration
procedure
Lack of
awareness of
the importance
of birth
registration
Lack of positive
and negative
incentives of
staff
Inadequate training
of staff for
birth registration
procedure/system
Birth registration not a priority for
government
Poor budget
allocation for
birth registration
Ethiopia, 2012

## Slide 13
This will generally include:
c
Strategic Planning is a disciplined approach to develop a multi-year vision of what results will be achieved and how they will be achieved
  Understanding the Causes of deprivations and Prioritizing issues to be addressed by UNICEF Action
  Establishing a Theory of Change (ToC) for the problem or deprivation
  Developing a Strategic Plan with a Results Framework
  Budgeting for Results
1
3
2
4
Strategic Planning
Notes: There are four main stages in the strategic planning process. This second step of the Strategic Planning process focuses on developing a theory of change that will establish how change will occur and results will be achieved.

## Slide 14
Understanding the Theory of Change Approach
A structured thinking process that allows groups to turn their theories or hypotheses about what needs to change and how into a “causal or change pathway”
A representation of how results will be achieved in a development undertaking and the markers that will permit measurement of whether or not a policy, programme or project remains on track.
Notes: Change initiatives are rarely straightforward processes, but happen through multiple and often unpredictable pathways with several aspects to the effort.
All programs are based on a set of assumptions or hypotheses about how the program should work. Sometimes this is clearly spelled out in programme documents. Sometimes it is only implicit and must be defined so it can be assessed.

## Slide 15
Understanding the Theory of Change Approach
Simply put…….“If X happens, then Y should happen”, because…
Explains what results will be achieved and how one level of results, such as outputs, leads to another level of results – outcomes
A set of and critical assumptions that make up a causal pathway of change forms the basis of the program design.
Notes: Change initiatives are rarely straightforward processes, but happen through multiple and often unpredictable pathways with several aspects to the effort.
All programs are based on a set of assumptions or hypotheses about how the program should work. Sometimes this is clearly spelled out in programme documents. Sometimes it is only implicit and must be defined so it can be assessed.

## Slide 16
Purpose
Essential to good RBM, as ToCs help organisations map the processes that contribute to desired change
Presents an easy-to-understand vision of how a desired result will be achieved
Presents a logical and realistic change pathway which guides the development of annual plans and activities
Test and demonstrate the programme logic
Essential tool for effective monitoring and evaluation

## Slide 17
Creating a Theory of Change
Articulation of a vision for change
FUTURE DESIRED SITUATION
CURRENT SITUATION
1
Notes: The first step in constructing a ToC requires the articulation of a vision of change—the future desired situation.
The vision of change provides a solution to an identified problem or issue. It is a situation in which child rights are met.
Articulating a vision of change derives from evidence, analytical work, and key programming references, such as child rights frameworks, the SDGs and/or national development frameworks.
This vision could be realized in the short, medium or long term, depending on the complexity of the problem.

## Slide 18
Creating a Theory of Change
Identification of necessary conditions for change
Medium term change - 1
Medium term change - 2
Medium term change - 3
2
FUTURE DESIRED SITUATION
CURRENT SITUATION
Hypotheses of how change
is likely to happen
Notes: The second step considers the conditions that must exist for the change to happen, as well as the hypotheses or pathways of how change is likely to happen (short and medium term changes).
Working from the future desired situation, conduct a ‘backwards mapping’ to identify the conditions that must exist, the things that need to be in place, to reach the future desired situation
Begin to formulate hypotheses or pathways of how change is likely to happen.
Developing hypotheses or pathways provides the “building blocks” for change. They examine the barriers and bottlenecks, as well as opportunities for achieving the vision.

## Slide 19
Creating a Theory of Change
3
Identification of actions to create conditions for change
FUTURE DESIRED SITUATION
CURRENT SITUATION
Short term change - 1
Short term change - 2
Short term change - 3
Activities
Activities
Activities
Activities
Activities
Medium term change - 1
Medium term change - 2
Medium term change - 3
Assumptions and Risks
Assumptions and Risks
Assumptions and Risks
Conditions for change
Notes: Change pathways lay the foundation for choices on areas for engagement, for establishing priority actions, and resource allocation.
Consideration of assumptions and risks through identification of the most important actors who will either promote the changes described or hinder them.
For country settings where risks related to disasters, climate change, conflict, epidemics or other shocks are high, the hypotheses must anticipate the ability to prevent or reduce risks through the choice of strategies.
Tracing out which action is likely to lead to another.

## Slide 20
CONTEXT
Creating a Theory of Change
Articulation of Interventions which contribute to the change effort
4
FUTURE DESIRED SITUATION
CURRENT SITUATION
Implementation Strategies that serve to achieve desired situation
Synergies
Between programme areas
Partnerships
Contribution of other partners to achieve desired
situation
CHANGE
RISKS
ASSUMP-TIONS
OPPORTU-NITIES
Notes: Based on considerations formulated in step 1-3; decide where UNICEF’s contribution will most likely support achievement of the outlined vision of change.
Select implementation strategies: on the basis of knowledge of context and evidence of what works; UNICEF’s comparative advantage; risks, considerations of sustainability, and the availability of UNICEF human and financial resources.
“Partnerships” is key implementation strategy, as –by definition- Outcome results are not achieved by UNICEF alone. Partnerships should show what other development partners are doing to achieve the desired change.
Consider and make explicit the synergies between the different programme areas

## Slide 21: Identifying Strategies
Strategies are key to building theories of change as they provide broad direction for how change happens, and directly influence the types of activities and interventions needed to achieve results.
The choice of strategy(ies) is based on:
  Awareness of how change is really achieved in the local context, including risks
  Considerations of effectiveness, sustainability, and availability of human and financial resources

## Slide 22: Identifying Strategies
See EXAMPLE: Strategies for UNICEF Strategic Plan 2018-2021:
Programming excellence- holistic approach/ winning support for cause of children/ developing and leveraging resources/ harnessing the power of business and markets for children/ United Nations working together/ Fostering innovations for children/ Harnessing the power of evidence as a driver of change

## Slide 23: Defining Assumptions
Assumptions are variables or factors which need to be in place for a result to be achieved
Examples:
  Other partners will successfully implement their own plans
  The national economy will improve as predicted
  Donors will provide needed OR funding to UNICEF
Notes: 23

## Slide 24: Defining Risks
Risks
A potential event or occurrence that could adversely affect the achievement of a desired result
Examples:
  Natural disasters, Conflict, Economic collapse
Risks are identified and classified according to 1) the likelihood of occurring, 2) their likely impact when they occur which is in turn influenced by the level of vulnerability and capacity to adequately respond.
Risk Formula
Shocks or Stresses x Exposure x Vulnerability
Capacity
Notes: 24
Essentially, risk to individuals, families, communities and systems, is about the probability of a crisis happening in the future, and what kind of impact it is likely to cause to humans, their assets, systems and infrastructure. Risk is a composite of several elements and for ease of understanding is commonly presented as the formula highlighted

## Slide 25
Creating a Theory of Change (example)
Articulation of a vision for change
Open defecation in no longer practiced in country X
Pervasive practice of open defecation, with many adverse consequences for children’s health
1
Notes: This example shows the current situation (problem, children’s rights are not met) and a vision for change (long-term solution to the problem, children’s rights are met)

## Slide 26
Creating a Theory of Change (example)
Identification of necessary conditions for change
Open defecation no longer practiced
Open defecation
2
The practice of defecating in the open is considered harmful by individuals and communities
Latrines and other sanitary options are accepted and regularly used
Availability of sanitation facilities that meet acceptable standards and in line with demand from households and communities
Notes: Medium-term changes or conditions that must exist / be in place, in order to reach the desired situation of ‘no more open defecation’ are formulated.

## Slide 27
Creating a Theory of Change (example)
3
Open defecation no longer practiced
Open defecation
Identification of actions to create conditions for change
Households and communities are aware of the negative consequences of open defecation
Community demand for improved sanitation facilities
Donor and partners make significant investments in sanitation
Assumption: community leaders are willing to promote healthy sanitation options
Risk: donors may prioritize other areas
Notes: Short-term changes that contribute to achieving the medium-term changes that must exist to reach the vision are formulated (can be more than 1 short-term change to contribute to achieving 1 medium-term change that must exist).
Assumptions and risks that may affect the programme are considered.

## Slide 28
Creating a Theory of Change (example)
Articulation of UNICEF’s contribution to the change effort
4
Implementation Strategies
Holistic approach/ / leveraging resources/ harnessing the power of markets for children/ Fostering innovations for children
Synergies
Health: advocacy re. latrine use
Education: promoting latrine use in schools
Partnerships
Government: investments in sanitation
UN Agencies: emergency preparedness
International and local NGOs: awareness raising on health benefits of latrines
Open defecation no longer practiced
Open defecation
Notes: Implementation Strategies that UNICEF will utilize are identified. (Implementation Strategies to be worked out in more detail in the narrative.)
Other development partners, how UNICEF works with them, and their respective contributions towards the desired situation are specified, so that it becomes clear how UNICEF and partners will jointly contribute towards achieving the desired situation.
Synergies between programme areas are outlined in the visual (and worked out in more detail in the narrative).

## Slide 29
Creating a Theory of Change (example)
5
Iteration and bringing it together
Strategies
Write a Narrative
IF communities are aware of the negative consequences of open defecation, THEN they will consider it a harmful practice
IF UNICEF conducts awareness raising sessions, THEN communities will be aware of the negative consequences of open defecation
IF open defecation is considered harmful, THEN open defecation is no longer practiced
Medium term change - 1
Short term change - 1
Open defecation no longer practiced
Open defecation
Notes: The ‘if-then’ logic is used to describe how change happens from one level of change to another.
For simplicity’s sake, this slide only shows ‘if-then’ logic for one of the medium-term changes to reach the vision, but of course this would need to be done for all conditions identified.

## Slide 30
Distinguishing ToC from Logframes
Theory of Change | Logical Framework
Critical thinking | Representation
Pathways of change | Lists relevant programme components
Explanation of how and why change occurs | Description of change elements
Adaptive and iterative relationships and influences | Linear and predictable cause-effect relationship
Articulates a strategic vision | Project management tool
Notes: Underline the critical thinking that encourages applying a ToC, focusing on the complexities of the desired change processes rather than the linear and systematic representation that the logframe entails.

## Slide 31: Strategic Planning
This will generally include:
c
Strategic Planning is a disciplined approach to develop a multi-year vision of what results will be achieved and how they will be achieved
  Understanding the Causes of deprivations and Prioritizing issues to be addressed by UNICEF Action
  Establishing a Theory of Change (ToC) for the problem or deprivation
  Developing a Strategic Plan with a Results Framework
  Budgeting for Results
1
3
2
4

## Slide 32: What is a result?
A result is a measurable or describable change arising
from a cause and effect relationship
A subject of change
A dimension of change
A qualifier of change
A RESULTS MUST HAVE
Notes: Example:
Number of children registered increased by 25% by 2019

## Slide 33: Recall on level of results
Long term changes in the situation of children and women
Nationally owned
Changes in behavior or performance of targeted individuals or institutions
Quality and coverage of services
UNICEF contributes to these changes
New products, skills, abilities and services
Changes in capacities of individuals or institutions
Attributable to programme funds and management – therefore high degree of accountability
IMPACT
OUTCOME
OUTPUT
Notes: E-learning will have contained exact definitions as will handouts
As results-based management is about change, worth being precise about for whom and where this change occurs. In human rights language – being specific about the subject of change (duty bearers or rights holders).

## Slide 34: Example of Levels of Results
IMPACT
OUTCOME
Stunting reduced
Improved
complementary feeding practice by mothers
OUTPUT
Improved knowledge and
awareness of mothers and caregivers
Notes: Assumption is that participants are already familiar with the definition of each results level. Make also reference to the glossary of key RBM terms.

## Slide 35: Accountabilities for the Achievement of Results
Focus
< 1 yr
< 3 yrs
3 - 5 yrs
Institutional
behaviour
Quality of Life
Individual behaviour
5 - 10 yrs
Reduced child mortality & morbidity
Health, education and community services functioning
Caretaker knows how to treat diarrhea
Mass media campaign on diarrhea
Like…
Caretaker treats child with ORS until diarrhea stops
Money, radio access,
Staff
Outcome
Impact
Output
Activity
Results
Outcome
Inputs
Timeline
10 -15 yrs
ACCOUNTABILITY
less
more
Operational/ skills, abilities,
products & services
Notes: This slide provides an example of levels of results, linked to estimated time frame needed to achieve them, and an indication that results at higher levels of the chain of results (outcomes and impact) can only be achieved through collaboration with a wide range of national and international partners. Individual accountability for results, diminishes the further up you go in the results chain

## Slide 36: Change Language
Action Language
Change Language
To promote child survival, physical and psychological development
To support the reduction of violence in schools
Children are alive, healthy, well nourished and active learners
By 2018, less than 5 percent of pupils in 3 targeted regions experience violence in schools
Notes: Note that in adopting a change language, i.e. focusing on the beneficiary, also the types of indicators you would define will be different. You will not try and monitor your activities, but you will focus on the effect these are expected to produce.

## Slide 37: Well-Stated Results Satisfy the SMART Criteria
S
Specific
M
Measurable
A
Achievable
R
T
Relevant
Time-bound
The result is clearly stated and described in change language, with as much detail as possible, leaving little room for confusion among different programme partners.
An assessment is possible to decide whether the result has been achieved, if possible in a quantifiable way. Qualitative assessments of results may also occur.
The result can feasibly be attained by the programme partners with through complementary efforts. All necessary resources are budgeted for and allocated. There are no major external factors, assumptions or risks which threaten the achievement of the result.
The expected result represents a milestone, or intermediate result in the chain, leading to strategic results for children and women.
The achievement of the result does not require an open-ended period. There is an expected date of accomplishment. For multi-year results, suitable indicators of progress should be defined.

## Slide 38: Indicators
Indicators are measures used to monitor progress made towards the achievement of intended results or the application of desired processes.
  Result statement: Within 3 years, 90% of girls enrolled in catch-up education courses are mainstreamed into primary schools
  Indicator: % of girls enrolled in catch-up education courses mainstreamed into primary schools
  Target Year 1: 45% of girls enrolled in catch-up education courses are mainstreamed into primary schools
  Performance of project in Year 1: 65% of girls enrolled in catch-up education courses are mainstreamed into primary schools
An indicator is neutral, does not pre-judge or set targets, is therefore “empty of data”, i.e., data still has to be collected
EXAMPLE

## Slide 39: Types of Indicators
Direct
Indirect / proxy
Indirect or "proxy" indicators demonstrate the change or results if direct measures are not feasible
Direct indicators correspond precisely to results at any performance level
Notes: These next three slides can be walked through very quickly, assuming that participants are already familiar with the issues.

## Slide 40: Types of Indicators
Qualitative observations
Standardised global indicators are comparable in all settings
Other indicators tend to be context specific and must be developed locally
Quantitative measures, expressed as percentage or share, as a rate, as a ratio

## Slide 41: Measurement Framework for Results
Results |  |  |  | 
Impact |  |  |  | 
Outcomes |  |  |  | 
Outputs |  |  |  | 
Vertical Logic
Impact
Outcomes
Outputs
Activities
Inputs
Notes: Frequently referred to as the Monitoring and Evaluation Framework – is used to systematically plan the collection of relevant information for monitoring, learning and reporting. The framework helps track the achievement of results.

## Slide 42: Measurement Framework for Results
Results | Performance Indicators | Baseline | Target | Means of Verification
Impact |  |  |  | 
Outcomes |  |  |  | 
Outputs |  |  |  | 
Horizontal Logic
Indicators
Baselines
Targets
Means of Verification
(Data Sources)
Notes: Frequently referred to as the Monitoring and Evaluation Framework – is used to systematically plan the collection of relevant information for monitoring, learning and reporting. The framework helps track the achievement of results.

## Slide 43: Going a step further
 |  |  |  | Frequency | Respon-sibility
Impact |  |  |  |  | 
Outcomes |  |  |  |  | 
Outputs |  |  |  |  | 
Results
Performance Indicators
Means of Verification
Data Collection Methods
Notes: Expanding the horizontal logic of the framework adding the frequency of data collection and related responsibilities for carrying it out. These elements should be reflected in operational monitoring and evaluation plans

## Slide 44: Baselines and Targets
The baseline is the status of the indicator at the beginning of an intervention
  Without a baseline we cannot tell if we are making progress
The target is the status of the indicator which is planned to be achieved at the end of the intervention
  Without a target we cannot tell if we have achieved the result
Notes: Note that the most common challenge in developing proper monitoring frameworks, is identifying the data for the baseline and set REALISTIC targets.
Invite participants to share reflections and experiences on the challenges to identify baselines and set targets. Some of the issues to be explored:
Data is not available – explore alternative ways to measure the baselines, expand your search of MoV, consider civil society’s sources ,etc.
Consider including in your programme activities to carry out a baselines study
Plan for a revision of the monitoring framework on a regular basis so that data can be updated
Consider trends and experiences from other contexts to set realistic, yet ambitious, targets.
Baseline:
Consider what are the sources of data?
What are the data collection methods?
Who will collect the data?
How often will the data be collected?
What is the cost and difficulty to collect the data?
Who will analyze the data?
Who will report the data?
Who will use the data?
Targets: Should be feasible given resource considerations and available capacity. Most are set annually, but some could be set quarterly. Others can be set for longer periods.

## Slide 45: Means of Verification (MoVs)
It is the means through which the status of an indicator is determined (e.g. existing information systems, survey, study, evaluation etc.)
The information source for the status of the indicator will define the frequency of indicator status updates (the indicator status can only be updated when new information on its status is available)
MoVs need to be reliable, practical and cost-efficient
Notes: Consider:
What are the sources of data?
What are the data collection methods?
Who will collect the data?
How often will the data be collected?
What is the cost and difficulty to collect the data?
Who will analyze the data?
Who will report the data?
Who will use the data?

## Slide 46: Strategic Planning
This will generally include:
c
Strategic Planning is a disciplined approach to develop a multi-year vision of what results will be achieved and how they will be achieved
  Understanding the Causes of deprivations and Prioritizing issues to be addressed by UNICEF Action
  Establishing a Theory of Change (ToC) for the problem or deprivation
  Developing a Strategic Plan with a Results Framework
  Aligning Results, Strategies and Funding
1
3
2
4

## Slide 47: RBM and Results Based Budgeting
Align resources required to results
Select strategies to implement the results
Identify Results
Define Indicators
Set baseline and targets
Modify results or strategies
Identify activities and inputs
Cost activities and inputs
Assess affordability
Not affordable/
Not aligned?
Results Based Management and Theory of Change
Resources Planning supported by costing of results

## Slide 48: Value-for-Money (VfM) (source: UNICEF PF4C training)
What is it?
The relationship between the resources spent on a programme and the results they buy
Why important?
Need to achieve biggest bang for buck
Evidence of good VfM can justify scale-up
When budgets are tight, good VfM will result in better results
Increasingly, donors require VfM before approving budgets to show aid is being well spent
Notes: Value for Money (see public finance for children training for fuller picture)

## Slide 49
Advancing the three Es in a programme strategy
Economy Best price for inputs (staff, services, supplies, etc)
  Examination of business processes to assure best price for procured inputs
Efficiency Achieving defined output through good value inputs
  Define realistic output results
  Programme strategy choices
  Aggregate cost of inputs that are transformed by sets of activities into outputs
Effectiveness Influence of outputs on achieving outcomes/impact
  Consideration of underlying costs to achieve results

## Slide 50: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning

## Slide 51: What are we managing when implementing under RBM?
Strategies and activities
Relationships with stakeholders
Implementing partners
Media and information
Financial resources
Human resources/staff
Supplies and equipment
Compliance with funding agreements
Internal processes
Risks
Knowledge

## Slide 52: What are we managing when implementing under RBM?
Strategies and activities (how related to results – are they sufficient and necessary?)
Relationships with stakeholders (Participation)
Implementing partners (Criteria in terms of results achievement and sustainability)
Media and information (Results focus)
Financial resources (value for money)

## Slide 53: What are we managing when implementing under RBM?
Human resources/staff (Capacity - RBM planning/ implementation
Supplies and equipment (Value for Money/ Equity/ Needs-based)
Compliance with funding agreements
Internal processes (efficiency/ effectiveness)
Risks (for achieving results)
Knowledge (what works for achieving results)

## Slide 54: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning

## Slide 55: Types of monitoring
MoRES Level 4
Key Management Questions
Are we implementing as planned ?
Are we achieving results ?
How is the situation of children or the wider context changing?
Implementation monitoring
Results monitoring
Situation monitoring
Types of Monitoring
Inputs
Activities
Outputs
Outcomes
Impact
Monitoring Focus
MoRES Level 2
Programmatic Visit (HACT)
Field Monitoring
MoRES Level 3
Notes: There are many additional labels for types of monitoring that fall in these categories.
Implementation monitoring – is the equivalent of Monitoring of Results for Equity System (MoRES) Level 2 monitoring, and both the Programmatic Visit under HACT Guidance, or Field Monitoring as it is called under the Programme Process guidance, focuses on the same level (inputs through to outputs).
The Spot Check, under HACT, by contrast focuses just at the level of inputs (not shown on the slide to avoid overload).
Results monitoring is roughly the equivalent to MoRES Level 3 monitoring.
Situation Monitoring is roughly the equivalent to MoRES Level 4 Monitoring

## Slide 56: Options in data collection methods/approaches
Systems
National Records Systems – EMIS, HIS
Participatory Approaches
Community reporting or scorecards
Sentinel systems
Field monitoring
Participatory Rural Appraisal, Visualization in Participatory Planning and variations
Qualitative methods
Observation
Focus groups
Key informant interviews
Surveys
Statistical – MICS, DHS
Purposive -- Sentinel site surveys
Notes: There are a wide range of methods, approaches and combinations of methods that can be used in monitoring. Some methods are actually packages of mixed-methods drawn together in an approach, like the participatory approaches discussed below. Some of the basic categories are:
Routine data systems are part of information management systems and subsystems that continuously collect information at different time periods (daily, weekly, monthly) and across different levels [individual (student, patient), administrative units (school, health center), and administrative levels (district, municipality)]. Routine data systems most commonly operate in education and health settings, such as Education Management Information Systems (EMIS) and Health Management Information Systems (HMIS), but they are increasingly being utilized in other areas, such as water supply and child protection (UNICEF, 2015) They offer full coverage of service points, but they are expensive to set up and cannot be changed easily. In addition to these traditional systems there are other ongoing data systems that can be more agile:
Sentinel surveillance: Sentinel surveillance involves repeat data collection from a sample of service delivery units or communities in selected areas or groups of people. Common examples include demographic sentinel site surveillance systems, ANC clinics as sentinel sites for HIV surveillance, nutritional surveillance and food security surveillance sentinel sites. Monitoring data from sentinel sites offers an indication of what is happening more broadly. Sentinel surveillance may be useful when indicators of interest but cannot be integrated into routine systems.
Field monitoring systems, such as third party monitoring systems which can be used for shorter periods or in contexts of weak government capacities to scale up monitoring.
Surveys: Surveys have been widely used in assessing access to, demand for and quality of service provision as well as higher level outcomes. Surveys typically use a questionnaire, administered by trained enumerators to collect data on variables of interest. Surveys such as MICS and DHS that are based on random sampling can offer robust data for statistical analysis (with confidence intervals depending on the sample size). Approaches with purposive sampling or combinations of purposive and then semi-random sampling can be undertaken where time and access constraints or gaps in sample frames do not allow for random surveys; for example, sentinel site surveys.
Qualitative methods include observation, focus groups and key informant interviews.
Observation is a basic method that It can include non-participant observation (observing participant(s) without actively participating) as well as participant observation (identifying the attitudes and practices of a community by living in the community). is often blended with other methods, for example in Field Monitoring Systems.
Key informant interview is an interviews with a person (or group of persons) with unique skills or professional background related to the issue/intervention being evaluated, who is knowledgeable about the project participants, or has access to other information of interest
Focus group interviews involve small discussions with 6 to 12 people who share certain characteristics and this both makes participants relatively more relaxed and more likely to discuss sensitive issues because of their common experience and able to represent a perspective of a certain group if FGs are repeated enough. They are useful for analysis of specific, complex problems, to identify attitudes and priorities in smaller groups.
Participatory methods: These approaches are particularly well suited for higher frequency data collection on changes in vulnerabilities and understanding access to demand for and quality of services at the local level. Participatory methods are used to strengthen accountability through community participation. A key characteristic is the combination of a variety of processes and techniques to collect, analyze and disseminate information, in ways that are accessible to citizens as well as able to influence donor and/or local and national policies. These often draw on the same methods as qualitative data collection and can also draw on surveys, but add techniques to help visualize collective analysis.
Citizen based monitoring/SMS technology monitoring: New methods for data collection and analysis supported by ICTs are fueling innovation around the production, delivery and presentation of local information for and by communities. The rise of citizen based monitoring is due to mobile phone technology, which has enabled individuals to perform monitoring functions.

## Slide 57: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning

## Slide 58: Reporting on Results - Purpose
Reports
Establish contributions made
Learning
Accountability
Notes: To establish that (if) UNICEF is achieving what it has set out to do—including the commitments made in programme documents (CPD, CPAP, Work Plans, etc.), and contributing to positive change for children
To account for its obligations viz-a-viz beneficiaries, the UNICEF Executive Board, governments and donors.
To account for how we use resources to achieve results
To learn and apply lessons within the programme and for other programmes
Reporting is integral to UNICEF’s mission
Preparation for reporting begins at the programme planning stage

## Slide 59: How we contribute to results
Result
Direct Actions
Result
UNICEF Actions
UNCT
Government Actions
Context, external factors
Contribution
Civil Society Actions
Attribution
Other Development Partners
Notes: FACILITATOR NOTES
The UNICEF Story is usually about how we contribute to the achievement of results for children. The complexity of actions needed to achieve results is reflected in the Theory of Change.
The challenge is to effectively tell the UNICEF Story of contribution without being overly:
>Complex in the analysis of the many factors that have led to change
>Simplistic and failing to recognize the contributions of other actors—especially governments, civil society, other development partners, and families of course
To meet these challenges, consider two simple tests:
>Will your grandmother understand the report?
>Will government and other institutions feel the report is balanced and fair to their own contribution (remember—your report will be available to them)
Be ready to acknowledge there are some instances (especially in humanitarian action) when direct attribution is possible. But challenge participants who hold to UNICEF attribution to consider that even in humanitarian action UNICEF almost always works with other development partners, governments and/or civil society organizations to achieve results.

## Slide 60: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning

## Slide 61: What is an Evaluation?
An evaluation is an assessment, as systematic and impartial as possible, of a programme, strategy, policy, sector, operational area or institutional performance
Evaluation aims to determine the relevance, efficiency, effectiveness, impact and sustainability of interventions
Evaluations provide credible evidence-based information, recommendations and lessons learned to improve future programming and decision making
Notes: The following questions are also quite relevant:
When do we plan for evaluations and why do we do so?
What management issues do we encounter in the conduct of evaluations and use of findings.

## Slide 62: Relationship between Evaluation and Monitoring
EVALUATION
MONITORING
Systematic, episodic
Systematic, ongoing
During or after implementation
During implementation
Appraisal of merit, value or
worth of a programme/
project/ intervention/ strategy
Tracking of programme/ project/activity progress
Assesses a programme’s
relevance, effectiveness,
efficiency, impact and
sustainability
For decision-making about
future actions
Accountability for results
Conducted by impartial
external evaluators
Assesses progress against activities defined in the Work Plan and Results level 2 & 3
For short term corrective action
Accountability for implementation
Conducted by programme
managers, partners or . external resources/monitors
Notes: Accountability for results
Evaluations provide an important source of evidence of the achievement of results and institutional performance and serve as a major means of verification for reporting on outcomes and outputs.
Evaluations help UNICEF and its partners better understand if resources are being used effectively and efficiently to improve equity.
To enhance accountability and transparency, evaluations should be conducted by independent experts, be widely shared and be issued as public documents in the public domain.
Organizational learning
Evaluations are important contributors to building knowledge and to organizational learning. Knowledge generated through evaluations provide critical input into major decisions that UNICEF and partners must take to improve performance and programming through informing key Country Programme milestones (Mid-Term Review, new Country Programme development, Strategic Moment of Reflection) when important choices must be made; assisting in the re-orientation of a programme due to shifts in the national context; and assessing pilots to determine if an initiative should go to scale. By supporting organizational learning and accountability, evaluation aims to help UNICEF to continually improve its achievement of results.
Knowledge generation
Understanding what works and what does not work and ensuring that lessons learned and emerging good practice are well-disseminated helps accelerate learning which can be introduced into other interventions.
Policy Advocacy
Knowledge generated through evaluation provides critical information in a timely manner to influence policy decisions to ensure that existing and future policies will enhance equity and improve the well-being of worst-off groups.
Evaluation provides evidence-based information that has the poten­tial to leverage major partner resources and political commitment for pro-equity programmes and policies.
Empowerment
Evaluations should aim to foster winder participation of stakeholders, including worst-off groups. By involving stakeholders in evaluation processes, evaluation can be empowering. It imparts skills, information and self-confidence to enhance the “evaluative thinking” of all. It can also strengthen the capacity of stakeholders to be evidence-based advocates.
National capacity development
UNICEF supports national capacity strengthening for monitoring (surveys, administrative data) as well as studies and evaluations, advocating for rigorous methods and compliance with M&E standards.
Countries (specifically, central and local authorities, governmental and civil society organizations) should own and lead their own national M&E systems.

## Slide 63: Types of Evaluation
Baseline
Reconsider,
redesign,
expand,
reduce, or
end
Formative/
Process
Evaluation
Ex-post/Summative/
Outcome/Impact
Evaluation (contribution)
On-going Monitoring
Evaluation
Framework
Ex-ante
Evaluation
Identify
a need
Design an
intervention
Initial
situation
OUTPUTS
OUTCOMES
Programme/
project start-up
Desired
result
Impact
Evaluation (attribution)
Design an Impact Evaluation
Is the programme evaluable or evaluation-ready?

## Slide 64: Key Elements of RBM
Evidence & Analysis
Implementation
Monitoring &
Reporting
Evaluation
Strategic Planning
Programme
Re-Design for Results
Notes: The key elements of the RBM include:
Strategic Planning —including analysis and prioritization to define areas of intervention
Resource Planning and Budgeting
Implementation
Monitoring
Reporting for accountability, transparency, advocacy and resource mobilization
Evaluation
Utilization of data, information and knowledge exchange for deepening a culture of evidence-based decision making
Continuous Change, Adaptability and Learning